## Gantt Chart
Working Period: 05 Jan 2026 – 27 Mar 2026 ¦ 58 working days
[8 empty] | Q1 | [12 empty] | Q2
Task | ID | Start | End | Duration | BW% | After | Dec 22 | Dec 29 | Jan 5 | Jan 12 | Jan 19 | Jan 26 | Feb 2 | Feb 9 | Feb 16 | Feb 23 | Mar 2 | Mar 9 | Mar 16 | Mar 23 | Mar 30 | Apr 6 | Apr 13 | Apr 20 | Apr 27 | May 4 | May 11 | May 18 | May 25 | Jun 1 | Jun 8 | Jun 15 | Jun 22 | Jun 29 | Jul 6
◆ Design Sign-off | M1 | 30-01-2026 | bar: Q1 Jan 26
◆ Beta Release | M2 | 15-04-2026 | bar: Q2 Apr 13
◆ GA Release |  | 01-06-2026 | bar: Q2 Jun 1
Core Backend ¦ Planned: 43d ¦ Available: 46d ¦ ✓ Under
Environment Setup | T0 | 05-01-2026 | 11-01-2026 | 3d | 100% |  | Q1 Jan 5: Environment Setup
Auth Service | T1 | 12-01-2026 | 01-02-2026 | 10d | 100% |  | Q1 Jan 12: Auth Service
User API | T2 | 02-02-2026 | 15-02-2026 | 8d | 100% | T1 | Q1 Feb 2: User API
Payment Gateway | T3 | 02-02-2026 | 22-02-2026 | 12d | 100% | T1 | Q1 Feb 2: Payment Gateway
Data Pipeline | T4 | 23-02-2026 | 15-03-2026 | 10d | 100% | T2, T3 | Q1 Feb 23: Data Pipeline
Frontend ¦ Planned: 32d ¦ Available: 58d ¦ ✓ Under
Design System | T5 | 05-01-2026 | 18-01-2026 | 8d | 100% |  | Q1 Jan 5: Design System
Dashboard | T6 | 19-01-2026 | 22-02-2026 | 10d | 50% | T5 | Q1 Jan 19: Dashboard
Checkout Flow | T7 | 23-02-2026 | 08-03-2026 | 8d | 100% | T5, T3 | Q1 Feb 23: Checkout Flow
Analytics View | T8 | 09-03-2026 | 22-03-2026 | 6d | 100% | T6, T7 | Q1 Mar 9: Analytics View
QA & Release ¦ Planned: 23d ¦ Available: 35d ¦ ✓ Under
Integration Tests | T9 | 23-03-2026 | 19-04-2026 | 10d | 100% | T4, T8 | Q1 Mar 23: Integration Tests
Performance Audit | T10 | 01-04-2026 | 10-05-2026 | 8d | 50% | T4 | Q2 Mar 30: Performance Audit
Release Prep | T11 | 11-05-2026 | 24-05-2026 | 5d | 100% | T9, T10 | Q2 May 11: Release Prep
On Hold ¦ Planned: 20d
Legacy Migration | T12 | 05-01-2026 | 11-01-2026 | 20d | 100% |  | Q1 Jan 5: Legacy Migration
Holidays
(unnamed) | 26-01-2026
(unnamed) | 20-03-2026